|  | Agreement for Performance of Work Services |
| --- | --- |

Terms of Reference

This Agreement for Performance of Work (APW) is requested by:

| Initiator: | Natalja Eigo | Reg.#: |  |
| --- | --- | --- | --- |
| Unit: | Performance, Planning and Economics (PPE) | Cluster / Dpt.: | HQ/HSD/PFD |

- *Purpose of the APW

The purpose of this APW is to enter into a contractual agreement with a successful bidder and select a suitable Contractor to carry out the following work: Develop a Data Management System (DMS) for Health Accounts, based on the functional requirements described in the RFP Annex 2 and built upon the existing Data Warehouse developed in WHO’s xMart. API requirements for data exchange with xMart are described in Annex 3 of the RFP.

- *Background

Health Accounts (HA) are a key policy instrument, for tracking health expenditure and informing health financing dialogue. The WHO HA team at WHO headquarters is very small, managing complex datasets from over 194 countries dating back to 2000. The volume and complexity of data continue to grow as demand for detailed information increases. The team, supported by regional and country offices, uses DMS to collect, store, consolidate, validate, and analyse country-provided data and to prepare for publication countries health expenditure data. The new tool should cover functionalities described in the Functional Requirements document attached as Annex 2 of this RFP.

- *Planned timelines (subject to confirmation)

Start date:  01/08/2026                                                             End date: 30/05/2027

Total duration: 10 months

- *Requirements - Work to be performed

Objective 1: Develop a first Pilot version of the Health Account’s Data Management System (DMS) that meets all the functionalities described in chapter 7 of the Requirements document attached in Annex 2 of this RFP.

Objective 1.1: Design and Development of DMS

The development of DMS is aimed to replace the legacy system with an online centralized platform, to support smooth data integration with external databases, advanced tools for data analysis and quality check, and support the entire lifecycle of the periodic publication of Health Accounts data of countries.

Implementation of this objective should be conducted in an Agile methodology, in 2-3 weeks long Sprint, where relevant. The deliverables should be deployed to the UAT (testing) environment first for verification by WHO experts, and then to the Production environment. Any bugs encountered in the Sprint should be fixed in the shortest period, within the current or next Sprint.

Under this objective, the Contractor is expected to perform the following activities:

- Technical and graphical design of the system, including the design of the prototype version and graphical representation of the system architecture.

- Phased development of the system according to the priorities and milestones agreed prior development.

- Quality assurance and testing.

- Training and handover.

- Hosting on the dedicated server/cloud and handover of source codes.

Objective 1.2: Integration with external databases

Under this objective the Contractor will perform a number of integrations with WHO internal and external databases, including xMart platform, to ensure the smooth and automated data exchange between DMS and external data sources. The data migration jobs will be established to periodic pull the data from remote servers and store them in the xMart database.

Objective 2: Based on the Pilot version, incrementally add the remaining functionalities described in the requirements document.

Objective 3: Cloud Infrastructure Support and Maintenance

As part of DMS operations, UAT and Production environments should be established and maintained. The Contractor will be required to perform support and maintenance of hosting Infrastructure of DMS, including maintenance of UAT and Production environments, 24/7 automated (not human based) monitoring of server performance and system accessibility, troubleshooting and configuration adjustment interventions as needed.

Tasks to be accomplished in the scope of this objective:

- Add / Remove cloud resources using Infrastructure as Code (IaC) and DevOps pipelines.

- Configuration and settings changes of Azure infrastructure components using IaC and DevOps pipelines.

- Monitoring of the cloud environment for stability and performance of the deployed infrastructure components as well as environment alerts.

- Monitor SSL certificate expiration date and update it timely to eliminate the risk of system downtime.

- Troubleshoot and support the provisioned Azure infrastructure.

- Contact Microsoft on behalf of WHO in case of any Cloud subscription or Cloud infrastructure related issues and get resolution/RCA (Root Cause Analysis).

The Contractor will be required to submit Support and Maintenance reports on a monthly basis, to indicate any changes and troubleshooting made to the UAT and Production environments.

Development and Methodology

It is highly recommended to apply the Agile methodology in the development of each Milestone. This will allow to split the scope of development Milestone into phased deliverables and present the outcomes of each sprint (release) by getting the comments and/or approval at the early stage. Collected comments should be applied in the sprints, without the need to redo major parts of the system by the end of the project.

The following steps should be followed during the implementation of this project:

- Technical requirement study of DMS. This activity will include the detailed study of all system requirements, and business processes for data import, analysis, verification and publication.

- Proposal on the system design, including wireframe/mockups of all modules of the system considering finding and requirements raised by WHO team.

- Proposal on the hardware requirements necessary to run the system.

- Receiving approval on the proposed design of all system modules.

- Development of DMS as per agreed workplan and schedule.

- Delivery of demo version of each milestone and deployment on UAT environment. Improvements based on received comments.

- Delivery of the final version of each milestone and deployment on Production environment.

- Training of system admins and key users.

- Delivery source codes, testing and completion reports, as well as technical documentation.

- Improvements during the 3 -months warranty period.

Testing, Training and Handover

Contractor will be required to perform comprehensive testing of the DMS, ensuring that all system modules are implemented according to the requirements and the in full compliance of acceptance criteria. WHO will take an active role in reviewing and verifying the functionality, user friendliness and the performance of the system. Any glitches, inconsistencies, or functional gaps identified during this process will be considered part of the project scope and must be resolved by the Contractor without additional cost or delay.

Contractor will be required to conduct thorough user and administrator training for the staff designated by WHO. These trainings should equip participants with the knowledge and skills necessary to operate, manage, and maintain the system effectively. By the end of the training period, WHO will issue user acceptance, confirming that the system meets the required standards and that staff are adequately prepared to use it.

Contractor will be required to hand over all system source codes and complete technical documentation, ensuring that WHO has full ownership and the ability to maintain or further develop the system in the future. The Completion Report should be submitted by the Contractor, summarizing all activities undertaken, deliverables produced, issues resolved, and final outcomes achieved under the project.

Warranty and Maintenance

The warranty period applies to all modules of DMS. During warranty period, the Contractor must ensure that all issues encountered, such as, bugs/errors and functionality change request must be resolved timely and ensure the smooth operation of the system. The warranty period should cover all feature enhancements, customizations, additional reports. In case of any new modifications or enhancements that can be completed within 10 working days by one staff member should be considered part of the project scope. Any requests requirements of more than 10 man-days of effort would be considered outside the scope and will be dealt separately. WHO and the Contractor will jointly determine such level of efforts and its priority.

During the development and the warranty period, up to 20% of scope adjustments of the scope should be acceptable.

Deliverables and Documentation

Throughout this project the Vendor should deliver the following outputs:

- System Design Document

- Wireframe/prototypes with UI/UX design

- Hardware requirement proposal

- Interim demonstrations

- Final demonstration

- Deployment of DMS on Production server

- Training of system users and administrators. Submission of Training Report

- Handover of database technical description, including relational schema, data types, table structures.

- Handover of source codes and related technical documentation, including the description of code files and system architecture diagram

- Handover of all third-party application license keys, if applicable

- Submission of Project Completion Report

- Handover of User and Administrator Guides

- *Requirements - Planning

| N | Description of Deliverables | Due Date | Payment (%) |
| --- | --- | --- | --- |
| 1 | - Technical and graphical design of the system, including prototypes delivered and accepted. - Hardware requirements for system hosting | 1 month from contract signing | 20 |
| 2 | - Development and acceptance of all system modules | 6 months from contract signing | 40 |
| 3 | - User acceptance testing; - Training - Deployment on WHO servers/cloud - Handover of source codes and technical documentation | 7 months from contract signing | 30 |
| 4 | - Warranty services (3 months) | 10 months from contract signing | 10 |

- Inputs

The WHO Health Accounts team will provide the information of requested services to be provided by the vendor as part of this agreement, plus any additional information that may be required for their efficient provision, meeting agreed quality levels.

- *Activity Coordination & Reporting

| Technical Officer: | Natalja Eigo Health Economist (HQ/HSD/PFD/PPE) | Email: | eigon@who.int |
| --- | --- | --- | --- |
| For the purpose of: | Technical supervision and instructions - Reporting |  |  |
| Administrative Officer: | Mr. Sorin BANICA Assistant to the unit, HQ/HSD/PFD/PPE | Email: | banicag@who.int |
| For the purpose of: | Contractual and financial management of the contract |  |  |

- *Characteristics of the Provider

WHO pays utmost attention to the level of qualification and experience of the Contractor and the allocated staff , as well as to the sustainability of the proposed solution and the continuity in the services.

  - Status

The Contractor shall be a for profit/ non for profit institution operating in the field of information technologies and business intelligence, with proven expertise in the successful development of expenditure/financial data solutions.

  - Accreditations

Accreditations or on-going accreditation processes by a certified accreditation body will be an asset.

- Certification ISO 9001:2015: Quality Management System

- Certification ISO/IEC 27000 family - Information security management systems

- Certifications within the Microsoft Certification Program including:

  - Microsoft Technology Associate (MTA)

  - Microsoft Certified Solutions Associate (MCSA)

  - Microsoft Certified Solutions Expert (MCSE)

  - Microsoft Solutions Developer (MCSD)

  - Previous experience

- Previous work with WHO, other international organizations and/or major institutions in the field of

  - Experience with xMart technology based development.

  - Econometrics and/or national health accounting is a plus.

  - Health expenditure data, health financing policy and overall health system operation and public finance system is a plus.

- Proven experience in

  - Successful development of expenditure/financial large or complex data solutions.

  - Business analysis experience:

    - Demonstrated professional experience documenting processes and seeing them used to drive added business value.

    - Demonstrated professional experience working with medium to large scale cross-functional processes in a global or international context.

    - Experience working within a project framework (Prince2 or PMI)

    - Experience with agile methods and design thinking.

  - Technical scope:

    - Cloud Architecture

    - Web Development w/ Microsoft technologies

    - Containerization

  - Good knowledge of statistical software such as SAS, STATA or R.

  - The experience and expertise of the selected Contractor company or consortium will require proof of delivery of similar fixed-price large projects (more than 1000 man-days).

  - The Contractor must be able to communicate a good standard of business English and all written deliverables will be in English.

  - Staffing

The Contractor should have a strong team of experts, with proven professional capacities. All experts who have a crucial role in implementing the scope of work are referred to as key experts. The Contractor shall submit CV’s and statements of exclusivity and availability for the key experts.

Other expert profiles (non-key) deemed relevant for the successful implementation of the project should be described and will be assessed in relation to the methodology and technical approach.

Key Expert 1: Project Manager

Qualifications and Skills:

- Master’s Degree in Computer Science, Management or Public Administration;

- Extensive knowledge of information system design and development strategies;

- Experience working within a project framework and corresponding certification (Prince2 or PMI) is a plus;

- Strong leadership and organizational abilities;

- Proven ability to work under pressure and handle multiple activities and tasks concurrently;

- Fluency in English is required, knowledge of another UN language is a plus;

- Strong analytical, research, report writing skills;

- Excellent communication, presentation and team work skills;

- Experience with agile methods and design thinking.

Professional experience:

- At least 7 years of professional experience in a relevant field;

- Experience in working as a team leader/project management in at least 3 projects of similar scope and complexity;

- Experience in developing analytical documents and reports;

- Experience in conducting user trainings.

Key Expert 2: Business Analyst

Qualifications and Skills:

- Master’s Degree in Business Management or Public Administration;

- Extensive knowledge of business analysis and development strategies;

- Out of box thinking and innovative approach;

- Good understanding of business needs and adaptation to the requirements;

- Proven ability to work under pressure and handle multiple activities and tasks concurrently;

- Fluency in English is required, knowledge of another UN language is a plus;

- Strong analytical, research, report writing skills;

- Excellent communication, presentation and team work skills.

Professional experience:

- At least 3 years of business analysis experience in a relevant field;

- Experience working on at least 2 successfully launched data management platforms.

- Experience in working as a team leader/project management in at least 3 projects of similar scope and complexity;

- Experience in developing analytical documents and reports;

- Experience in conducting user trainings.

Key Expert 3: Technical Lead

Qualifications and Skills:

- Master’s Degree in Computer Science, Engineering or relevant field.

- Extensive understanding of development and customization of data management platforms.

- Experience with securely collecting and standardizing data from multiple sources to produce high quality data and advanced analytics.

- Proven technical leadership skills, with track-record to lead a team of experts.

- Proven ability to work under pressure and handle multiple activities and tasks concurrently.

- Excellent technical, diagnostic, and troubleshooting skills.

- Fluency in English is required, knowledge of another UN language is a plus;

- Strong analytical, research, mentorship skills.

- Excellent communication, motivational, and interpersonal skills.

Professional experience:

- At least 5 years of professional experience in a relevant field.

- Experience as a technical lead/senior developer in at least 3 projects of similar scope and complexity.

- Experience in software developing methodologies and information systems analysis.

- Experience in leading the development of information systems, deployment, training and handover.

- Experience in understanding the customer needs and flexibility in adapting the solution.

- Experience in development and customization of data management platforms.

- Certifications within the Microsoft Certification Program or equivalent will be considered as a plus, including:

- Microsoft Technology Associate (MTA)

- Microsoft Certified Solutions Associate (MCSA)

- Microsoft Certified Solutions Expert (MCSE)

- Microsoft Solutions Developer (MCSD)

Key Expert 4: Senior Software Engineer

Qualifications and Skills:

- Degree in Computer Science, Engineering or relevant field.

- Proficiency with fundamental front-end languages such as HTML, CSS, and JavaScript.

- Familiarity with JavaScript frameworks such as Angular JS, React, and Amber.

- Proficiency with server-side languages such as Python, Ruby, Java, PHP, and .Net.

- Familiarity with database technology such as MySQL, MS SQL, Oracle, and MongoDB.

- Familiarity with the development and customization of e-learning platforms.

- Good problem-solving skills.

- Attention to details.

Professional experience:

- At least 5 years of professional experience as senior engineer or system architect.

- Experience as a system architect/senior developer in at least 3 projects of similar scope and complexity.

- Experience in designing system framework, database architecture, microservice infrastructure.

- Experience in system optimization and data management algorithms.

- Microsoft Solutions Developer (MCSD) certificate or equivalent will be considered as a plus.

Key Expert 5: Data Analyst

Qualifications and Skills:

- Degree in Computer Science, Information Management, Statistics, or relevant field.

- Technical expertise regarding data models, database design development, data mining and segmentation techniques.

- Good knowledge of statistical software such as SAS, STATA or R.

- Strong knowledge of and experience with reporting packages (Business Objects etc), databases (SQL etc), programming (XML, Javascript, or ETL frameworks).

- Knowledge of statistics and experience using statistical packages for analyzing datasets (Excel, SPSS, SAS etc.)

- Strong analytical skills with the ability to collect, organize, analyze, and disseminate significant amounts of information with attention to detail and accuracy.

- Good problem-solving skills.

Professional experience:

- At least 5 years of professional experience as a data analyst or business data analyst.

- Experience as a data analyst in at least 3 projects of similar scope and complexity.

- Experience in system optimization and data management algorithms

- Experience in health accounts data management is a plus.

Key Expert 6: Product Designer

Qualifications and Skills:

- Degree in Design, Human–Computer Interaction, Information Systems, or related field; certification in UX/UI design desirable.

- Proven skills in user-centered design, including prototyping, wireframing, and usability testing.

- Proficiency with modern design tools and knowledge of front-end frameworks.

- Ability to design intuitive, accessible, and user-friendly interfaces for complex data systems.

- Strong understanding of data visualization, dashboards, and reporting design.

- Excellent communication and facilitation skills to gather user requirements and translate them into design solutions.

Professional Experience:

- Minimum 5 years of experience designing user interfaces for IT tools or platforms, ideally in international or public health contexts.

- Demonstrated portfolio of successful system designs that improved usability, accessibility, and user adoption.

- Experience collaborating with developers and policy teams to align design with both technical requirements and user needs.

- Prior experience with health, economic, or statistical data systems is a strong asset.

Key Expert 7: DevOps Engineer

Qualifications and Skills:

- Degree in Computer Science, Information Management, Statistics, or a relevant field.

- Must have effective communication with excellent logic and problem solving skills and a drive to make a difference;

- Ability to understand and communicate customer issues;

- In-depth knowledge of the Microsoft platform (IIS, .NET, Web Services, SQL Server, SharePoint, Windows Server, Clustering, Active Directory etc.);

- Well versed with Azure DevOps (VSTS) is a plus.

Professional experience:

- At least 5 years of CI/CD, DevOps experience with a good understanding of Software configuration Management.

- Proficiency with Cloud services (AKS, Azure Functions, API Management, etc.), containerization (Docker, Kubernetes), and infrastructure as code (Terraform).

- Strong experience with GitLab CI/CD pipelines, shell scripting, and automation tools (Ansible, Jenkins).

- Familiarity with database management (PostgreSQL, MySQL, Mongo) and scripting languages (Python, Groovy).

- Knowledge of monitoring, APM tools (Datadog, Pager Duty), and experience with security and compliance in a cloud environment.

- Supporting Azure cloud deployments, including API management and container orchestration with Kubernetes.

- Troubleshooting and resolving issues in code deployments and maintaining the operational integrity of digital operations.

- Well versed with Azure offerings with work experience on the same like Web apps, ASE, ASP, function apps, SQL PaaS, and Storage accounts;

- Microsoft DevOps Engineer certification is a plus.

Short-term non-key experts

The Contractor should provide other short-term experts as required for the design and development of the DMS. The pool of other experts (such as Database Engineers, Software Engineers, UI/UX Designers, Quality Assurance Engineers, Trainers, Technical Writers, etc.) should include a good mix of experiences and know-how to complement the key experts in delivering on the tasks. These profiles must indicate whether they are to be regarded as senior/junior so that it is clear which fee rate in the budget breakdown will apply to each profile.

- *Place of assignment

This assignment will be implemented remotely (outside of WHO campuses). The Contractor must however be reachable during business hours in Geneva, Switzerland as the WHO PPE team requires.

While the execution of this APW is in progress, travel may be possible for tasks that require on-site presence, the scope of which will be defined later by the WHO PPE team.  Any travel costs associated with potential on-site tasks will be reviewed separately from the main financial proposal.

This template is only to be used for APWs granted to Companies, and not for APWs granted to Individuals.